## Whereabouts
ALL WHEREABOUTS MUST BE SUBMITTED TO construction@ukpowerdistribution.co.uk BY 4PM THURSDAY FOR WORKS THE FOLLOWING WEEK.
Week Commencing: |  |  |  | 2025-09-30
Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Sat |  | Sun |  | Activity | UKPD Reference number | Site Address : | Developer | Description of works | ICP | ICP Site contact name & number |  | Site Contact Name & Number |  | Live Electric Jointing | Fusing | Single / 3 Phase | Works Completed?
AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | [6 empty] | Name | Number | Name | Number
Use the Group Colour Code from the table of activities below | [13 empty] | Use the Activity Group Abbreviation from the table below | 6 x digits beginning 2….. Or UKPRJ |  |  |  | Your companies name | Your companies Project Manger |  | The contact for the site (eg contractor)
R | R | [12 empty] | ST Dom | For example pupose only - UKPD123456 | Example Address and Postal Code | Example ICP customer | Example: IDNO substation Name and LV Panel Way number. LIVE JOINTING 3c300mm service breach joints x 3 to feed streetlights No 4-5-6 and plots 29-30-31 testing, fusing. Aslaid and closure pack to follow. | ICP Name | Project Manager |  | Jointer |  | Y | 1 Phase
Activitiy Group
Group 1 |  | Ex |  |  | Excavation Works
|  | Duct |  |  | Ducting Installation
|  | SUB B |  |  | Substation Base Casting
|  | SUB CIV |  |  | Substation Civil Work
|  | SUB ED |  |  | Substation Equipment - Delivery
Group 2 |  | CL HV |  |  | Cable Laying High Voltage
|  | CL LV |  |  | Cable Laying Low Voltage
|  | SL |  |  | Cable Laying Service
Group 3 |  | MJ HV |  |  | HV Jointing
|  | MJ LV |  |  | LV Jointing
|  | SJ |  |  | Service Jointing
|  | ST Dom |  |  | Service Terminations 100 Amp Single Phase
|  | ST 3PH |  |  | Service Terminations 3 Phase Single supply)
|  | ST Mul |  |  | Service Terminations Multiway (MOD 16/Bemco type)
|  | ST 11 |  |  | Service Terminations 11kV
|  | TERM |  |  | Substation Equipment - Termination
|  | CT HV-LV |  |  | Cable testing HV or LV
|  | EARTH |  |  | Substation Equipment- Earthing
|  | PRE-COMM |  |  | Switchgear Pre-commissioning
|  | ENERG |  |  | Live Working / Fusing / Jointing / Linking / Cut-Out Replacement
|  | PLOT ENERG |  |  | PLOT Energisation Request (Fusing / Jointing / Service Connections / Live Working)
* ENERG - Requires formal energisation request submission (WD 5 days LV, WD 10 days HV) * PLOT ENERG - Requires works package information n whereabouts only

## Sheet2 (hidden)
Y | 3 Phase | G
N | 1 Phase | B
Ex |  | R
Duct
SUB B
SUB CIV
SUB ED
CL HV
CL LV
SL
MJ HV
MJ LV
SJ
ST Dom
ST 3PH
ST Mul
ST 11
TERM
CT HV-LV
EARTH
PRE-COMM
A
ENERG
PLOT ENERG